## Sheet1
[5 empty] | Current |  |  | November 19- December 2 |  |  | December 3-December 8
Progress | Test | Requirement Verification | Description |  | Component Level | Integration |  | Subsystem | Integration |  | Full System
0% | End of Semester Test Demo | All Level 1 Requirements | End of Year Test | 75% | Initial Camera Test |  | 18.75% | Guidance Subsystem |  | 19.3% | End of Semester Test Demo
0% | Tracking/ID Subsystem | 1.1, 2.1, 2.2, 8.2, 8.3, 8.4 | Test full Tracking Subsystem | 5% | Target Imaging
0% | Guidance Subsystem | 1.2, 5.2, 7.2 | Test full Guidance Subsystem | 10% | Obstacle Perceived
0% | Planning Subsystem | 1.2, 5.2, 5.3 | Test full Planning Subsystem | 10% | Obstacle Map
0% | Controls Subsystem | 1.2, | Test full Controls Subsystem | 25% | Visual Odometry Verification and Characterization
25% | Hardware Subsystem | 5.1, 8.1 | Test full Hardware Subsystem
75% | Initial Camera Test | 1.1.1,1.1.2 | Record images, load into processing software | 5% | Human Target ID |  | 14.25% | Tracking/ID Subsystem
5% | Target Imaging | 1.1.3 | Correctly locate targets 95% of time | 25% | Target Estimation
5% | Human Target ID | 1.1.5 | Experiment with human ID at various distances | 25% | Multiple targets
25% | Collision Correction | 1.2.1 | Send system on collision course, verify avoidance | 15% | Target Estimate Update
75% | Trajectory Test | 1.2.2, 1.2.3 | Give trajectory to desired position, verify accuracy with VICON | 25% | Target Accuracy and Range
25% | Obstacle Avoidance | 1.2.4 | Maintain a distance of 5 cm from obstacles, verify with VICON
50% | Durataion | 1.3.1, 1.3.2 | Endurance test, while searching, full payload. Measure Distance traveled as well | 25% | Collision Correction |  | 21% | Planning Subsystem
25% | Target Estimation | 2.1.1 | Estimate position to withing 0.5 meters | 75% | Trajectory Test
25% | Multiple targets | 2.1.2 | At least 2 targets estimated and ID | 25% | Obstacle Avoidance
15% | Target Estimate Update | 2.2.1 | Track targets, each updated position should be 10 Hz | 10% | Receive and Transmit Test
90% | Autonomous Takeoff & Landing | 3.1.2, 3.1.3 | Self Explainitory | 5% | Communications
25% | Payload | 5.1.1 | Self Explainitory
10% | Receive & Transmit Test | 7.1.1, 7.1.2 | Send and receive data packets | 25% | Collision Correction |  | 40.31% | Controls Subsystem
10% | Obstacle Perceived | 7.2.1, 7.2.2 | Report obtacle locations, verify with VICON | 75% | Trajectory Test
10% | Obstacle Map | 7.3.1 | Obstacle Map maintained | 25% | Obstacle Avoidance
5% | Communications | 7.3.2, 7.4.1 | Communicate Obstacle Maps and Confirmed target tracks | 90% | Autonomous Takeoff & Landing
25% | Target Accuracy and Range | 8.3.1, 8.3.2 | Detect tags at 95% accuracy, find the maximum distance
25% | Visual Odometry Verification and Characterization | 1.2, 1.1 | SLAM accuracy and positioning | 50% | Durataion |  | 34.38% | Hardware Subsystem
|  |  |  | 25% | Payload