## Sheet1
Item | Status | Completed | Issued | Owners | Task Level | Description | Notes
1 | closed | 2015-09-04 | 2015-09-01 | Austin/Drew |  | Meet with sponsors | Attendance of other team members is optional
2 | closed | 2015-09-08 | 2015-09-01 | Steve |  | Make a vicon tutorial | Should be accessible to all with no vicon/linux experience
3 | closed | 2015-09-08 | 2015-09-01 | All |  | Have VM installed
19 | closed | 2015-09-09 | 2015-09-09 | Drew | High | Contact Dr. Frew and James about purchasing | Reference Steve's parts list and a bluetooth telecon tool
close | 2015-09-15 | 2015-09-01 | Steve | Low | Lit. Rev.: Visual Odometry / SLAM | Cheap lens parametrization, strategies for mitigating bad effects of cheap cameras
close | 2015-09-15 | 2015-09-01 | Austin | Low | Lit. Rev: Radio tracking/Indoor Flight/Cntrl. | Radio beacons for localization
close | 2015-09-15 | 2015-09-01 | Bryce | Low | Lit. Rev.: Indoor Flight/Cntrl. | Adaptive controls (L1 flight control?) evaluation needed, this is what IntelinAir uses
close | 2015-09-15 | 2015-09-01 | Tyler | Low | Lit. Rev.: SLAM | Adaptive controls (L1 flight control?) evaluation needed, this is what IntelinAir uses
close | 2015-09-15 | 2015-09-01 | Matt | Low | Lit. Rev: SLAM
close | 2015-09-15 | 2015-09-01 | Taylor | Low | Lit. Rev.: SLAM
close | 2015-09-15 | 2015-09-01 | Prashant | Low | Lit. Rev: Swarm Flight
close | 2015-09-15 | 2015-09-01 | Ed | Low | Lit. Rev.: Visual Odemetry | Flight strategies for using visual odemetry in control loop. I believe BYU has some good papers on this.
close | 2015-09-15 | 2015-09-01 | Drew | Low | Lit. Rev. : Sensor Fusion/Estimation | BYU papers, UKFs, etc.