## Sheet1
Item | Status | Due | Issued | Owners | Task Level | Description | Notes
1 | open | 2015-09-15 | 2015-09-02 | Matt, Tyler, Taylor | Medium | Get quadrotor flying and pull data | Use vicon tutorial from Steve to pull data while quad is flying, import into matlab
2 | open | 2015-09-16 | 2015-09-08 | Controls Team | High | Develop controller models | Presentation will be made to Dr. Frew on 9-15
3 | open | 2015-09-23 | 2015-09-08 | Nav. Team | High | Prototype SLAM Algorithm on Laptop | Presentation will be made to Dr. Frew on 9-23
4 | open | 2015-09-16 | 2015-09-09 | Drew/Austin | High | Create requirements document | Should flow down from given customer description
5 | close | 2015-09-16 | 2015-09-09 | Drew | Medium | Create integration team | Should consist of one member of each current subteam lead by the SE
6 | open | 2015-09-16 | 2015-09-09 | Nav. Team | High | Perform trade study on camera sensor setup, onboard computers, and rangefinders
7 | open | 2015-09-16 | 2015-09-09 | Controls Team (Prashant) | Medium | Perform trade study on autopilots | Accelerometer performance, gyro performance, and computing power
8 | open | 2015-09-16 | 2015-09-09 | Nav. Team | High | Perform trade studies on SLAM solutions | Reference map errors, position estimate errors, and projected run rate
9 | open | 2015-09-16 | 2015-09-09 | Drew/Austin | Medium | Follow up with Zohaib on questions listed in 9/9 minutes
10 | open | 2015-09-16 | 2015-09-09 | Drew | High | Complete purchase orders on onboard PCs and sensors | Reference Steve's parts list and a bluetooth telecon tool
11 | review | 2015-09-16 | 2015-09-09 | All | High | Review project charter | Send revisions and suggestions to Drew
12
13
14
15
16
17
18
19
20