## Sheet1
[5 empty] | Current-November 18 |  |  | November 19- December 2 |  |  | December 3-December 8
Progress | Test | Requirement Verification | Description |  | Component Level | Integration |  | Subsystem | Integration |  | Full System
0% | End of Semester Test Demo | All Level 1 Requirements | End of Year Test | 0% | Initial Camera Test |  | 0% | Guidance Subsystem |  | 1.406% | End of Semester Test Demo
0% | Tracking/ID Subsystem | 1.1, 2.1, 2.2, 8.2, 8.3, 8.4 | Test full Tracking Subsystem | 0% | Target Imaging
0% | Guidance Subsystem | 1.2, 5.2, 7.2 | Test full Guidance Subsystem | 0% | Obstacle Perceived
0% | Planning Subsystem | 1.2, 5.2, 5.3 | Test full Planning Subsystem | 0% | Obstacle Map
0% | Controls Subsystem | 1.2, | Test full Controls Subsystem
0% | Hardware Subsystem | 5.1, 8.1 | Test full Hardware Subsystem | 0% | Human Target ID |  | 0% | Tracking/ID Subsystem
0% | Initial Camera Test | 1.1.1,1.1.2 | Record images, load into processing software | 0% | Target Estimation
0% | Target Imaging | 1.1.3 | Correctly locate targets 95% of time | 0% | Multiple targets
0% | Human Target ID | 1.1.5 | Experiment with human ID at various distances | 0% | Target Estimate Update
0% | Collision Correction | 1.2.1 | Send system on collision course, verify avoidance | 0% | Target tag identification
0% | Trajectory Test | 1.2.2, 1.2.3 | Give trajectory to desired position, verify accuracy with VICON | 0% | Target Accuracy and Range
0% | Obstacle Avoidance | 1.2.4 | Maintain a distance of 5 cm from obstacles, verify with VICON | 0% | Unique Target Tags
0% | Durataion | 1.3.1, 1.3.2 | Endurance test, while searching, full payload. Measure Distance traveled as well
0% | Target Estimation | 2.1.1 | Estimate position to withing 0.5 meters | 0% | Collision Correction |  | 0% | Planning Subsystem
0% | Multiple targets | 2.1.2 | At least 2 targets estimated and ID | 0% | Trajectory Test
0% | Target Estimate Update | 2.2.1 | Track targets, each updated position should be 10 Hz | 0% | Obstacle Avoidance
50% | Autonomous Takeoff & Landing | 3.1.2, 3.1.3 | Self Explainitory | 0% | Delivery Zone
0% | Payload | 5.1.1 | Self Explainitory | 0% | Communications
0% | Delivery Zone | 5.2.1 | Within 5 meters of confirmed target | 0% | Receive & Transmit Test
0% | Payload Delivery | 5.3.1, 5.3.2 | Release and confirm payload delivered safely | 0% | Payload Delivery
0% | Receive & Transmit Test | 7.1.1, 7.1.2 | Send and receive data packets
0% | Obstacle Perceived | 7.2.1, 7.2.2 | Report obtacle locations, verify with VICON | 0% | Collision Correction |  | 9.375% | Controls Subsystem
0% | Obstacle Map | 7.3.1 | Obstacle Map maintained | 0% | Trajectory Test
0% | Communications | 7.3.2, 7.4.1 | Communicate Obstacle Maps and Confirmed target tracks | 0% | Obstacle Avoidance
0% | Target tag identification | 8.2.1 | Roport identified tags | 50% | Autonomous Takeoff & Landing
0% | Target Accuracy and Range | 8.3.1, 8.3.2 | Detect tags at 95% accuracy, find the maximum distance
0% | Unique Target Tags | 8.4.1 | Report tag ID numbers of all identified targets | 0% | Durataion |  | 0% | Hardware Subsystem
|  |  |  | 0% | Payload
Pushed To Next Semester