## Sheet1
Item | Status | Completed | Issued | Owners | Task Level | Description | Notes
1 | closed | 2015-09-04 | 2015-09-01 | Austin/Drew |  | Meet with sponsors | Attendance of other team members is optional
2 | closed | 2015-09-08 | 2015-09-01 | Steve |  | Make a vicon tutorial | Should be accessible to all with no vicon/linux experience
3 | closed | 2015-09-08 | 2015-09-01 | All |  | Have VM installed
19 | closed | 2015-09-09 | 2015-09-09 | Drew | High | Contact Dr. Frew and James about purchasing | Reference Steve's parts list and a bluetooth telecon tool