## Sheet1
Item | Status | Due | Issued | Owners | Task Level | Description | Notes
1 | open | 2015-09-15 | 2015-09-01 | Steve | Low | Lit. Rev.: Visual Odometry / SLAM | Cheap lens parametrization, strategies for mitigating bad effects of cheap cameras
2 | open | 2015-09-15 | 2015-09-01 | Austin | Low | Lit. Rev: Radio tracking/Indoor Flight/Cntrl. | Radio beacons for localization
3 | open | 2015-09-15 | 2015-09-01 | Bryce | Low | Lit. Rev.: Indoor Flight/Cntrl. | Adaptive controls (L1 flight control?) evaluation needed, this is what IntelinAir uses
4 | open | 2015-09-15 | 2015-09-01 | Tyler | Low | Lit. Rev.: SLAM | Adaptive controls (L1 flight control?) evaluation needed, this is what IntelinAir uses
5 | open | 2015-09-15 | 2015-09-01 | Matt | Low | Lit. Rev: SLAM
6 | open | 2015-09-15 | 2015-09-01 | Taylor | Low | Lit. Rev.: SLAM
7 | open | 2015-09-15 | 2015-09-01 | Prashant | Low | Lit. Rev: Swarm Flight
8 | open | 2015-09-15 | 2015-09-01 | Ed | Low | Lit. Rev.: Visual Odemetry | Flight strategies for using visual odemetry in control loop. I believe BYU has some good papers on this.
9 | open | 2015-09-15 | 2015-09-01 | Drew | Low | Lit. Rev. : Sensor Fusion/Estimation | BYU papers, UKFs, etc.
10 | open | 2015-09-15 | 2015-09-02 | Matt, Tyler, Taylor | Medium | Get quadrotor flying and pull data | Use vicon tutorial from Steve to pull data while quad is flying, import into matlab
11 | open | 2015-09-16 | 2015-09-08 | Controls Team | High | Develop controller models | Presentation will be made to Dr. Frew on 9-15
12 | open | 2015-09-23 | 2015-09-08 | Nav. Team | High | Prototype SLAM Algorithm on Laptop | Presentation will be made to Dr. Frew on 9-23
13 | open | 2015-09-16 | 2015-09-09 | Drew/Austin | High | Create requirements document | Should flow down from given customer description
14 | open | 2015-09-16 | 2015-09-09 | Drew | Medium | Create integration team | Should consist of one member of each current subteam lead by the SE
15 | open | 2015-09-16 | 2015-09-09 | Nav. Team | High | Perform trade study on camera sensor setup, onboard computers, and rangefinders
16 | open | 2015-09-16 | 2015-09-09 | Controls Team (Prashant) | Medium | Perform trade study on autopilots | Accelerometer performance, gyro performance, and computing power
17 | open | 2015-09-16 | 2015-09-09 | Nav. Team | High | Perform trade studies on SLAM solutions | Reference map errors, position estimate errors, and projected run rate
18 | open | 2015-09-16 | 2015-09-09 | Drew/Austin | Medium | Follow up with Zohaib on questions listed in 9/9 minutes
19 | open | 2015-09-16 | 2015-09-09 | Drew | High | Complete purchase orders on onboard PCs and sensors | Reference Steve's parts list and a bluetooth telecon tool
20 | review | 2015-09-16 | 2015-09-09 | All | High | Review project charter | Send revisions and suggestions to Drew