## Sheet1
Status | Completed | Issued | Owners | Task Level | Description | Notes
closed | 2015-09-04 | 2015-09-01 | Austin/Drew |  | Meet with sponsors | Attendance of other team members is optional
closed | 2015-09-08 | 2015-09-01 | Steve |  | Make a vicon tutorial | Should be accessible to all with no vicon/linux experience
closed | 2015-09-08 | 2015-09-01 | All |  | Have VM installed
closed | 2015-09-09 | 2015-09-09 | Drew | High | Contact Dr. Frew and James about purchasing | Reference Steve's parts list and a bluetooth telecon tool
close | 2015-09-15 | 2015-09-01 | Steve | Low | Lit. Rev.: Visual Odometry / SLAM | Cheap lens parametrization, strategies for mitigating bad effects of cheap cameras
close | 2015-09-15 | 2015-09-01 | Austin | Low | Lit. Rev: Radio tracking/Indoor Flight/Cntrl. | Radio beacons for localization
close | 2015-09-15 | 2015-09-01 | Bryce | Low | Lit. Rev.: Indoor Flight/Cntrl. | Adaptive controls (L1 flight control?) evaluation needed, this is what IntelinAir uses
close | 2015-09-15 | 2015-09-01 | Tyler | Low | Lit. Rev.: SLAM | Adaptive controls (L1 flight control?) evaluation needed, this is what IntelinAir uses
close | 2015-09-15 | 2015-09-01 | Matt | Low | Lit. Rev: SLAM
close | 2015-09-15 | 2015-09-01 | Taylor | Low | Lit. Rev.: SLAM
close | 2015-09-15 | 2015-09-01 | Prashant | Low | Lit. Rev: Swarm Flight
close | 2015-09-15 | 2015-09-01 | Ed | Low | Lit. Rev.: Visual Odemetry | Flight strategies for using visual odemetry in control loop. I believe BYU has some good papers on this.
close | 2015-09-15 | 2015-09-01 | Drew | Low | Lit. Rev. : Sensor Fusion/Estimation | BYU papers, UKFs, etc.
closed | 2015-09-16 | 2015-09-08 | Controls Team | High | Develop controller models | Presentation will be made to Dr. Frew on 9-15
close | 2015-09-16 | 2015-09-09 | Drew | Medium | Create integration team | Should consist of one member of each current subteam lead by the SE
closed | 2015-09-16 | 2015-09-09 | Nav. Team | High | Perform trade study on camera sensor setup, onboard computers, and rangefinders
closed | 2015-09-21 | 2015-09-16 | Tyler | HIGH | Get project charter signed by appropriate parties
closed | 2015-09-16 | 2015-09-09 | All | High | Review project charter | Send revisions and suggestions to Drew
2015-09-16 | 2015-09-09 | Drew | High | Complete purchase orders on onboard PCs and sensors | Reference Steve's parts list and a bluetooth telecon tool