## Sheet1
Item | Status | Due | Issued | Owners | Description | Notes
1 | open | 2015-09-23 | 2015-09-02 | Matt, Tyler, Taylor | Get quadrotor flying and pull data | Use vicon tutorial from Steve to pull data while quad is flying, import into matlab
2 | open | 2015-09-23 | 2015-09-08 | Nav. Team | Prototype and perform trade studies SLAM Algorithms on Laptop/Hardware | Presentation will be made to Dr. Frew on 9-23. RGBD and LiDAR solutions
3 | review | 2015-09-25 | 2015-09-09 | Drew/Austin | Create requirements document | Should flow down from given customer description
4 | open | 2015-09-23 | 2015-09-09 | Controls Team (Prashant) | Perform trade study on autopilots | Accelerometer performance, gyro performance, and computing power
5 | open | 2015-09-30 | 2015-09-16 | Austin | Layout ROS/system architecture
6 | open | 2015-09-23 | 2015-09-16 | Ed | MATLAB quadrotor modelling demo
7 | open | 2015-09-30 | 2015-09-16 | Drew | Get turtlebots running
8 | open | 2015-09-25 | 2015-09-16 | Prashant | Pixhawk Controller Modelling | Implement pixhawk controller in matlab, email script to Drew by Friday
9 | open | 2015-09-30 | 2015-09-23 | Bryce | Position Interface Pixhawk | Includes running SIL Sim with ROS
10 | open | 2015-09-30 | 2015-09-23 | Ed | Model Development
11 | open | 2015-09-30 | 2015-09-16 | Matt | Interface ODROID with Pixhawk | Talk to Bryce about messages that have to be sent.
12 | open | 2015-10-07 | 2015-09-23 | Bryce, Matt | Spoof GPS Data from Vicon, close position control loop
13
14
15
16
17