## Sheet1
Status | Completed | Issued | Owners | Description | Notes
closed | 2015-09-04 | 2015-09-01 | Austin/Drew | Meet with sponsors | Attendance of other team members is optional
closed | 2015-09-08 | 2015-09-01 | Steve | Make a vicon tutorial | Should be accessible to all with no vicon/linux experience
closed | 2015-09-08 | 2015-09-01 | All | Have VM installed
closed | 2015-09-09 | 2015-09-09 | Drew | Contact Dr. Frew and James about purchasing | Reference Steve's parts list and a bluetooth telecon tool
closed | 2015-09-15 | 2015-09-01 | Steve | Lit. Rev.: Visual Odometry / SLAM | Cheap lens parametrization, strategies for mitigating bad effects of cheap cameras
closed | 2015-09-15 | 2015-09-01 | Austin | Lit. Rev: Radio tracking/Indoor Flight/Cntrl. | Radio beacons for localization
closed | 2015-09-15 | 2015-09-01 | Bryce | Lit. Rev.: Indoor Flight/Cntrl. | Adaptive controls (L1 flight control?) evaluation needed, this is what IntelinAir uses
closed | 2015-09-15 | 2015-09-01 | Tyler | Lit. Rev.: SLAM | Adaptive controls (L1 flight control?) evaluation needed, this is what IntelinAir uses
closed | 2015-09-15 | 2015-09-01 | Matt | Lit. Rev: SLAM
closed | 2015-09-15 | 2015-09-01 | Taylor | Lit. Rev.: SLAM
closed | 2015-09-15 | 2015-09-01 | Prashant | Lit. Rev: Swarm Flight
closed | 2015-09-15 | 2015-09-01 | Ed | Lit. Rev.: Visual Odemetry | Flight strategies for using visual odemetry in control loop. I believe BYU has some good papers on this.
closed | 2015-09-15 | 2015-09-01 | Drew | Lit. Rev. : Sensor Fusion/Estimation | BYU papers, UKFs, etc.
closed | 2015-09-16 | 2015-09-08 | Controls Team | Develop controller models | Presentation will be made to Dr. Frew on 9-15
closed | 2015-09-16 | 2015-09-09 | Drew | Create integration team | Should consist of one member of each current subteam lead by the SE
closed | 2015-09-16 | 2015-09-09 | Nav. Team | Perform trade study on camera sensor setup, onboard computers, and rangefinders
closed | 2015-09-21 | 2015-09-16 | Tyler | Get project charter signed by appropriate parties
closed | 2015-09-16 | 2015-09-09 | All | Review project charter | Send revisions and suggestions to Drew
closed | 2015-09-16 | 2015-09-09 | Drew | Complete purchase orders on onboard PCs and sensors | Reference Steve's parts list and a bluetooth telecon tool
closed | 2015-09-25 | 2015-09-23 | Steve | Reflash team computer
cancelled | 2015-09-25 | 2015-09-16 | Prashant | Pixhawk Controller Modelling | Implement pixhawk controller in matlab, email script to Drew by Friday
closed | 2015-09-23 | 2015-09-09 | Prashant | Perform trade study on autopilots | Accelerometer performance, gyro performance, and computing power
closed | 2015-09-29 | 2015-09-02 | Matt, Tyler, Taylor | Get quadrotor flying and pull data | Use vicon tutorial from Steve to pull data while quad is flying, import into matlab
closed | 2015-09-23 | 2015-09-08 | Perception Team | Prototype and perform trade studies SLAM Algorithms on Laptop/Hardware | Presentation will be made to Dr. Frew on 9-23. RGBD and LiDAR solutions
closed | 6-Oct | 1-Oct | Drew | Purchasing round 2