## Sheet1
Item | Status | Due | Issued | Owners | Description | Notes
1 | open | 2015-09-04 | 2015-09-01 | Austin/Drew | Meet with sponsors | Attendance of other team members is optional
2 | open | 2015-09-21 | 2015-09-01 | All | Scope document | Will be based on current understanding of requirements from Joe Tanners slides until further clarification is obtained from UTRC
3 | open | 2015-09-08 | 2015-09-01 | Steve | Make a vicon tutorial | Should be accessible to all with no vicon/linux experience
4 | open | 2015-09-08 | 2015-09-01 | All | Have VM installed
5 | open | 2015-09-15 | 2015-09-01 | Steve | Lit. Rev.: Visual Tracking/Odometery/Lens | Cheap lens parametrization, strategies for mitigating bad effects of cheap cameras
6 | open | 2015-09-15 | 2015-09-01 | Austin | Lit. Rev: Radio tracking/Indoor Flight/Cntrl. | Radio beacons for localization
7 | open | 2015-09-15 | 2015-09-01 | Bryce | Lit. Rev.: Indoor Flight/Cntrl. | Adaptive controls (L1 flight control?) evaluation needed, this is what IntelinAir uses
8 | open | 2015-09-15 | 2015-09-01 | Tyler | Lit. Rev.: Indoor Flight/Cntrl. | Adaptive controls (L1 flight control?) evaluation needed, this is what IntelinAir uses
9 | open | 2015-09-15 | 2015-09-01 | Matt | Lit. Rev: Swarm Flight
10 | open | 2015-09-15 | 2015-09-01 | Taylor | Lit. Rev.: Swarm Flight/Vis. Od.
11 | open | 2015-09-15 | 2015-09-01 | Prashant | Lit. Rev: Swarm Flight
12 | open | 2015-09-15 | 2015-09-01 | Ed | Lit. Rev.: Visual Odemetry | Flight strategies for using visual odemetry in control loop. I believe BYU has some good papers on this.
13 | open | 2015-09-15 | 2015-09-01 | Drew | Lit. Rev. : Sensor Fusion/Estimation | BYU papers, UKFs, etc.