## Sheet1
Item | Status | Due | Issued | Owners | Description | Notes
1 | review | 2015-09-25 | 2015-09-09 | Drew/Austin | Create requirements document | Should flow down from given customer description
2 | open | 2015-09-30 | 2015-09-16 | Austin | Layout ROS/system architecture
3 | open | 2015-10-20 | 2015-09-16 | Ed | MATLAB quadrotor modelling demo
4 | open | 2015-10-20 | 2015-09-16 | Drew | Get turtlebots running
5 | open | 2015-10-07 | 2015-09-23 | Bryce/Steve | Position Interface Pixhawk | Includes running SIL Sim with ROS
6 | open | 2015-10-07 | 2015-09-16 | Bryce/Steve | Interface ODROID with Pixhawk | Talk to Bryce about messages that have to be sent.
7 | open | 2015-10-07 | 2015-09-23 | Bryce/Steve | Spoof GPS Data from Vicon, close position control loop
8 | open | 2015-10-07 | 2015-09-23 | Perception Team | Run RTAB map on Tegra/ODROID in flight envrionment
9 | open | 2015-10-07 | 2015-09-23 | Austin | Block diagram for perception team
10 | open | 2015-10-20 | 2015-09-26 | Matt | Develop final flight demo design
11 | open | 2015-10-07 | 2015-09-28 | Taylor/Matt | Mass vs Endurance Testing. Pull Vicon data
12 | open | 2015-10-07 | 2015-09-28 | Prashant | LiDAR and Ultrasonic Hardware testing
13 | open | 2015-10-07 | 2015-09-28 | Drew | Purchasing Round 2
14 | open | 2015-10-07 | 2015-09-28 | Taylor | Target tracking prototyping
15 | open | 2015-10-07 | 2015-09-28 | Tyler | Power Budget
16 | open | 2015-10-07 | 2015-09-28 | Matt | Hardware Modifications | Blade guards, sensor mounts, etc.