## Sheet1
Item | Status | Due | Issued | Owners | Task Level | Description | Notes
1 | open | 2015-09-23 | 2015-09-02 | Matt, Tyler, Taylor | Medium | Get quadrotor flying and pull data | Use vicon tutorial from Steve to pull data while quad is flying, import into matlab
3 | open | 2015-09-23 | 2015-09-08 | Nav. Team | High | Prototype and perform trade studies SLAM Algorithms on Laptop/Hardware | Presentation will be made to Dr. Frew on 9-23. RGBD and LiDAR solutions
4 | review | 2015-09-16 | 2015-09-09 | Drew/Austin | High | Create requirements document | Should flow down from given customer description
7 | open | 2015-09-23 | 2015-09-09 | Controls Team (Prashant) | Medium | Perform trade study on autopilots | Accelerometer performance, gyro performance, and computing power
9 | open | 2015-09-16 | 2015-09-09 | Drew/Austin | Medium | Follow up with Zohaib on questions listed in 9/9 minutes
10 | open | 2015-09-16 | 2015-09-09 | Drew | High | Complete purchase orders on onboard PCs and sensors | Reference Steve's parts list and a bluetooth telecon tool
11 | review | 2015-09-16 | 2015-09-09 | All | High | Review project charter | Send revisions and suggestions to Drew
12 | open | 2015-09-30 | 2015-09-16 | Austin | Medium | Layout ROS/system architecture
13 | open | 2015-09-18 | 2015-09-16 | Drew | Medium | Email Zohaib
14 | open | 2015-09-23 | 2015-09-16 | Ed | Medium | MATLAB quadrotor modelling demo
15 | open | 2015-09-30 | 2015-09-16 | Controls Team | Medium | Bryce add stuff here
16 | open | 2015-09-21 | 2015-09-16 | Tyler | HIGH | Get project charter signed by appropriate parties
17
18
19
20