## Sheet1
[7 empty] | Now - February 29 |  |  | March 1 - April 17 |  |  | April 18 - End Of Semester
Progress | Test | Requirement Verification | Description | Min People Required | To Be Completed by |  | Component Level | Integration |  | Subsystem | Integration |  | Full System
0% | End of Semester Test Demo | All Level 1 Requirements | End of Year Test |  | 2016-02-01 | 0% | Initial Camera Test |  | 0% | Guidance Subsystem |  | 8.438% | End of Semester Test Demo
0% | Tracking/ID Subsystem | 1.1, 2.1, 2.2, 8.2, 8.3, 8.4 | Test full Tracking Subsystem |  | 2016-02-22 | 0% | Target Imaging
0% | Guidance Subsystem | 1.2, 5.2, 7.2 | Test full Guidance Subsystem |  | 2016-02-29 | 0% | Obstacle Perceived
0% | Planning Subsystem | 1.2, 5.2, 5.3 | Test full Planning Subsystem |  | 2016-02-15 | 0% | Obstacle Map
0% | Controls Subsystem | 1.2, | Test full Controls Subsystem |  | 2016-02-08 | 0% | Visual Odometry Verification and Characterization
0% | Hardware Subsystem | 5.1, 8.1 | Test full Hardware Subsystem
0% | Initial Camera Test | 1.1.1,1.1.2 | Record images, load into processing software |  | 2016-02-22 | 0% | Human Target ID |  | 0% | Tracking/ID Subsystem
0% | Target Imaging | 1.1.3 | Correctly locate targets 95% of time |  | 2016-02-08 | 0% | Target Estimation
0% | Human Target ID | 1.1.5 | Experiment with human ID at various distances |  | 2016-02-29 | 0% | Multiple targets
0% | Collision Correction Planning | 1.2.1 | Send system on collision course, verify avoidance |  | 2016-02-15 | 0% | Target Estimate Update
0% | Trajectory Test Planning | 1.2.2, 5.2 | Give trajectory to desired position, verify accuracy with VICON |  | 2016-02-01 | 0% | Target Accuracy and Range
0% | Obstacle Avoidance Planning | 1.2.4 | Maintain a distance of 5 cm from obstacles, verify with VICON
75% | Durataion | 1.3.1, 1.3.2 | Endurance test, while searching, full payload. Measure Distance traveled as well |  | 2016-02-15 | 0% | Collision Correction Planning |  | 0% | Planning Subsystem
0% | Target Estimation | 2.1.1 | Estimate position to withing 0.5 meters |  | 2016-02-01 | 0% | Trajectory Test Planning
0% | Multiple targets | 2.1.2 | At least 2 targets estimated and ID |  | 2016-02-08 | 0% | Obstacle Avoidance Planning
0% | Target Estimate Update | 2.2.1 | Track targets, each updated position should be 10 Hz |  | 2016-02-22 | 0% | Receive and Transmit Test
0% | Autonomous Takeoff & Landing | 3.1.2, 3.1.3 | Self Explainitory |  | 2016-02-29 | 0% | Communications
75% | Payload | 5.1.1 | Self Explainitory
0% | Receive & Transmit Test | 7.1.1, 7.1.2 | Send and receive data packets |  | 2016-02-29 | 0% | Collision Correction Controls |  | 0% | Controls Subsystem
0% | Obstacle Perceived | 7.2.1, 7.2.2 | Report obtacle locations, verify with VICON |  | 2016-02-15 | 0% | Trajectory Test Controls
0% | Obstacle Map | 7.3.1 | Obstacle Map maintained |  | 2016-02-22 | 0% | Obstacle Avoidance Controls
0% | Communications | 7.3.2, 7.4.1 | Communicate Obstacle Maps and Confirmed target tracks |  | 2016-02-08 | 0% | Autonomous Takeoff & Landing
0% | Target Accuracy and Range | 8.3.1, 8.3.2 | Detect tags at 95% accuracy, find the maximum distance
0% | Visual Odometry Verification and Characterization | 1.2, 1.1 | SLAM accuracy and positioning | 2 | 2016-02-01 | 75% | Durataion |  | 56.25% | Hardware Subsystem
0% | Collision Correction Controls |  |  | 2 | 2016-02-01 | 75% | Payload
0% | Trajectory Test Controls
0% | Obstacle Avoidance Controls